## Sheet1
ID | Phase & Task Description | Sub-Tasks / Technical Requirements | Complexity | Est. MD
0.0 | Document Pre-processing |  |  | 3.0
0.1 | Document Loader Adapter | Implement support for local/S3 file loading and Mime-type validation. |  | 0.5
0.2 | Page Splitting Logic | Logic to split multi-page PDFs into individual images/sub-PDFs for processing. |  | 0.5
0.3 | Parallel OCR Orchestration | Implementation of concurrent page-level OCR using Azure DI. |  | 1.0
0.4 | OCR Result Aggregator | Merging page-level text, confidence, and metadata into a unified document object. |  | 0.5
0.5 | Pre-processing Unit Tests | Validation of splitting, merging, and handling of corrupted/blurred files. |  | 0.5
1.0 | Architecture & Foundation |  |  | 3.5
1.1 | Graph State Design | Define `GraphState`, Pydantic schemas for node outputs. |  | 0.5
1.2 | Logprob Analyzer Engine | Implement math logic for Margin calculation and confidence normalization. |  | 1.0
1.3 | OCR Integration Layer | Implement Azure DI wrapper with `ainvoke` support and error handling. |  | 0.5
1.4 | Infrastructure Utilities | Setup Structlog, Pydantic-settings, and LangSmith tracing. |  | 1.0
1.5 | Base Unit Tests | Setup pytest for core utility functions (Logprob, OCR). |  | 0.5
2.0 | Taxonomy & Specialist Nodes |  | High | 6.0
2.1 | Root Router Implementation | Prompt engineering for MED vs NON classification. |  | 1.0
2.2 | Medical Specialist (Sub-codes) | Implement medical node; Prompt tuning for LAB, CHK, OTH. | * | 2.0
2.3 | Non-Med Specialist (Sub-codes) | Implement non-med node; Prompt tuning for ID, PAS, OTH. | * | 2.0
2.4 | Pydantic Output Validation | Implement strict schema validation for LLM classification codes. |  | 0.5
2.5 | Node Logic Unit Tests | Unit tests with Mocked LLM responses to verify fallback logic and logprob extraction. |  | 0.5
3.0 | Active Labeling Strategy |  |  | 5.5
3.1 | Pilot Batch Processing | Script to run 1,000+ docs through current pipeline; export data. |  | 1.0
3.2 | Verification Tooling | Build Streamlit UI for fast human verification (Image vs Prediction). |  | 1.5
3.3 | Human Labeling Execution | (External) Users verify predictions to create Gold Standard labels. | * | 2.0
3.4 | Ground Truth Sanitization | Script to resolve label conflicts and clean final evaluation set. |  | 1.0
4.0 | Reliability Engineering |  | High | 6.0
4.1 | Confusion Matrix Analysis | Evaluate against Gold Standard; find high False Positive classes. |  | 1.0
4.2 | Margin Threshold Optimization | Plot precision/recall curves to find the optimal Margin Threshold. |  | 2.0
4.3 | Prompt Conflict Resolution | Re-tune prompts to fix overlaps found during evaluation. | * | 2.0
4.4 | Failure Case Documentation | Create "Negative Examples" dataset for targeted performance tuning. |  | 1.0
5.0 | API Layer & Wrapper |  |  | 2.0
5.1 | FastAPI Endpoints | `/classify` (async), `/health`, and metadata endpoints. |  | 1.0
5.2 | Validation Middleware | Input validation (File size, Mime type) and Global Exception Handling. |  | 0.5
5.3 | Integration Docs | Generate Swagger/Redoc and provide Client-side SDK samples. |  | 0.5
TOTAL |  |  |  | 26.0 MD